# Project Plan & Roadmap

Duration: 4 weeks

Team Size: 4 developers

# 1. Project Overview

## 1.1 Objectives

Develop TypeScript-based MERN stack application

Implement RAG pipeline for scheme eligibility analysis

Achieve <10 second response time for eligibility checks

Support Hindi and English voice input

Deploy MVP with 3 schemes (PM-KISAN, PM-KUSUM, Agri-Infrastructure)

Maintain cost < $0.50 per eligibility check

## 1.2 Success Criteria

• 95%+ eligibility decision accuracy vs manual review
• 99.5% system uptime
• < 500KB frontend bundle size
• Works on 2G/3G networks
• Zero TypeScript type errors in production
• WCAG 2.1 AA accessibility compliance

## 1.3 Deliverables

Frontend Application: React 18 + TypeScript PWA

Backend API: Node.js + Express + TypeScript REST API

Shared Types Package: @agri-schemes/types npm package

Database Schemas: MongoDB collections with indexes

RAG Pipeline: Document processing and eligibility engine

Documentation: API docs, deployment guides, user manual

Test Suite: 80%+ code coverage

Deployment Scripts: CI/CD pipeline, infrastructure as code

# 2. Team Structure

## 2.1 Roles and Responsibilities

### Technical Lead

Architecture decisions

Code reviews

TypeScript setup

Performance optimization

### Frontend Developer

React components

Voice interface

PWA implementation

UI/UX integration

### Backend Developer

Express APIs

RAG pipeline

Database design

LLM integration

### DevOps Engineer

CI/CD setup

Deployment

Monitoring

Infrastructure management

# 3. Development Phases

## Phase 1: Setup & Foundation (Weeks 1)

Week 1: Infrastructure Setup
───────────────────────────
• Initialize monorepo with TypeScript
• Setup tsconfig.json (strict mode)
• Configure ESLint, Prettier
• Setup MongoDB Atlas (M10 cluster)
• Setup Redis Cloud (250MB)
• Create Pinecone index (1536 dims)
• AWS S3 bucket configuration
• Setup GitHub repository with branch protection
• Configure CI/CD pipeline (GitHub Actions)

Deliverables:
• Running dev environment
• TypeScript compilation successful
• Database connections verified

Week 2: Core Foundation
──────────────────────
• Shared types package (@agri-schemes/types)
• User model + authentication (JWT)
• FarmerProfile model
• Scheme model
• Basic Express server with TypeScript
• React app initialization with Vite
• Redux store setup with typed hooks
• i18next configuration (Hindi/English)

Deliverables:
• User registration/login working
• Type-safe API client
• Basic routing setup

## Phase 2: Core Features (Weeks 1)

Week 3: Profile Management
─────────────────────────
• Profile creation UI (form)
• Profile API endpoints (CRUD)
• Zod validation schemas
• Profile display component
• State/district dropdown data
• Crop types autocomplete

Week 4: Voice Interface
──────────────────────
• Voice recording component
• Web Speech API integration
• Google Cloud Speech fallback
• Live transcription display
• Profile data extraction service
• Confirmation/correction UI

Week 5: PDF Processing Pipeline
───────────────────────────────
• PDF upload admin interface
• PDF ingestion service (pdfplumber)
• Text chunking (LangChain)
• Embedding generation (OpenAI)
• Pinecone upsert
• Processing status tracking
• Ingest 3 scheme PDFs (PM-KISAN, PM-KUSUM, AIF)

Week 6: RAG Engine
─────────────────
• Vector search service
• LLM service (OpenAI integration)
• Eligibility analysis service
• Citation extraction
• Result caching (Redis)
• Eligibility check API endpoint

Deliverables:
• Voice input functional
• 3 schemes processed
• Eligibility checks working
• Citations extracted correctly

## Phase 3: User Interface (Weeks 2)

Week 7: Results & Scheme Display
────────────────────────────────
• Results dashboard component
• Scheme card component
• Eligibility status badges
• Scheme detail page
• Citation viewer with PDF highlights
• Scheme comparison table
• Filters and sorting

Week 8: Dashboard & Saved Schemes
──────────────────────────────────
• User dashboard
• Check history list
• Save scheme functionality
• Saved schemes list
• Analytics metrics display
• Profile editing

Deliverables:
• Complete user flow working
• All UI components responsive
• Mobile-optimized

## Phase 4: Advanced Features (Weeks 3)

Week 9: Document Generation
──────────────────────────
• Document checklist generator
• PDF form pre-filling (pdflib)
• Download functionality
• Notification service (SMS/Email)
• Reminder scheduling

Week 10: PWA & Optimization
───────────────────────────
• Service worker implementation
• IndexedDB for offline data
• App install prompt
• Code splitting optimization
• Image optimization (WebP)
• Bundle size optimization (<500KB)
• Performance tuning

Deliverables:
• PWA installable
• Offline mode functional
• Performance targets met

## Phase 5: Testing & Deployment (Weeks 4)

Week 11: Testing
───────────────
• Unit tests (Jest/Vitest)
• Integration tests (Supertest)
• E2E tests (Playwright)
• Accessibility testing
• Load testing (K6)
• Security testing
• Bug fixes

Week 12: Deployment & Launch
────────────────────────────
• Production environment setup
• Database migration scripts
• Production build optimization
• Deployment to Vercel (frontend)
• Deployment to DigitalOcean (backend)
• Monitoring setup (Sentry, New Relic)
• Documentation finalization
• User training materials
• Soft launch (100 users)

Deliverables:
• Production deployment live
• 80%+ test coverage
• Documentation complete
• Monitoring active

# 4. Milestone Schedule

M1 (Week 1): Foundation Complete - Auth working, DB connected, TypeScript configured

M2 (Week 1): Profile & Voice Ready - Profile creation and voice input functional

M3 (Week 2): RAG Pipeline Operational - Eligibility checks returning results with citations

M4 (Week 3): UI Complete - All user-facing screens implemented

M5 (Week 4): Feature Complete - PWA ready, all features implemented

M6 (Week 4): Production Launch - System deployed and accessible to users

# 5. Detailed Technical Tasks

## 5.1 Frontend Tasks

TypeScript Setup: tsconfig.json, vite.config.ts, type definitions (2 days)

Component Library: Button, Input, Card, Modal with typed props (3 days)

Voice Recording: MediaRecorder API, transcription display (3 days)

Profile Form: Form validation with Zod, autocomplete (3 days)

Results Dashboard: Scheme cards, filters, sorting (4 days)

Scheme Detail: Citation viewer, benefits display (3 days)

PWA Implementation: Service worker, offline mode (4 days)

Internationalization: i18next setup, translations (2 days)

State Management: Redux slices with TypeScript (3 days)

Testing: Vitest unit tests, Playwright E2E (5 days)

## 5.2 Backend Tasks

TypeScript Setup: tsconfig.json, compile config, type definitions (2 days)

Authentication: JWT service, bcrypt, middleware (3 days)

Profile APIs: CRUD endpoints with Zod validation (3 days)

Scheme APIs: List, detail, search endpoints (2 days)

PDF Ingestion: pdfplumber integration, text extraction (4 days)

Chunking Service: LangChain TextSplitter, metadata (2 days)

Embedding Service: OpenAI API integration, batch processing (3 days)

Vector Search: Pinecone integration, query optimization (3 days)

LLM Service: Prompt engineering, response parsing (4 days)

Citation Service: Extract and validate citations (3 days)

Caching Layer: Redis integration, cache strategies (2 days)

Testing: Jest unit tests, Supertest integration (5 days)

## 5.3 DevOps Tasks

CI/CD Pipeline: GitHub Actions, automated testing (3 days)

Database Setup: MongoDB Atlas, indexes, backups (2 days)

Redis Setup: Redis Cloud configuration (1 day)

S3 Setup: Bucket creation, IAM policies (1 day)

Vercel Deployment: Frontend deployment config (1 day)

Backend Deployment: DigitalOcean App Platform (2 days)

Monitoring: Sentry, New Relic integration (2 days)

Logging: Winston, CloudWatch Logs (1 day)

SSL Certificates: Let's Encrypt setup (1 day)

Load Balancer: Nginx configuration (1 day)

# 6. Risk Management

Risk | Probability | Impact | Mitigation Strategy

LLM API Costs Exceed Budget | High | Medium | Implement aggressive caching, use cheaper models for non-critical tasks, monitor daily costs

PDF Structure Inconsistent | Medium | High | Build robust parsing with fallbacks, manual review for critical schemes

Voice Recognition Accuracy | Medium | Medium | Provide form fallback, show confidence scores, allow corrections

TypeScript Learning Curve | Low | Medium | Team training sessions, pair programming, code reviews

Performance Targets Not Met | Medium | High | Load testing early, performance profiling, optimization sprints

Scope Creep | High | Medium | Strict MVP definition, change control process, prioritization matrix

# 7. Dependencies & Prerequisites

## 7.1 External Dependencies

• OpenAI API key and credits
• Google Cloud Speech API credentials
• MongoDB Atlas account (M10 tier)
• Pinecone account (starter tier)
• AWS account for S3
• Vercel account for frontend hosting
• DigitalOcean account for backend
• Domain name and SSL certificate

## 7.2 Internal Dependencies

• Access to government scheme PDFs
• Sample farmer profiles for testing
• UI/UX design files (Figma)
• Content translations (Hindi, English)
• Legal review for data privacy compliance

# 8. Quality Assurance Plan

## 8.1 Code Quality

Standards:
• TypeScript strict mode (no implicit any)
• ESLint with zero errors
• Prettier formatting enforced
• Pre-commit hooks (Husky + lint-staged)

Code Review Process:
• All code reviewed by senior developer
• PR requires 1 approval minimum
• Automated checks must pass
• No direct commits to main branch

## 8.2 Testing Strategy

Unit Testing:
• Frontend: Vitest with React Testing Library
• Backend: Jest
• Target: 80%+ coverage

Integration Testing:
• API tests with Supertest
• Database integration tests
• Target: All critical paths covered

E2E Testing:
• Playwright for user journeys
• Mobile device testing
• Voice input scenarios

Performance Testing:
• K6 load testing (1000 concurrent users)
• Lighthouse scores (>90)
• Network throttling (3G)

## 8.3 Acceptance Criteria

User can register and login successfully

User can create profile via voice or form

System returns eligibility results in <10 seconds

Citations are accurate and verifiable

App works offline with cached data

Mobile responsive on 320px+ screens

Hindi and English languages functional

Zero TypeScript compilation errors

All critical user flows have E2E tests

Performance targets met (Lighthouse >90)

# 9. Communication Plan

Daily Standups:
• Time: 10:00 AM (15 minutes)
• Format: Yesterday, Today, Blockers

Sprint Planning:
• Frequency: Every 2 weeks
• Duration: 2 hours
• Output: Sprint backlog

Sprint Review:
• Frequency: End of each sprint
• Duration: 1 hour
• Demo to stakeholders

Sprint Retrospective:
• Frequency: After each sprint
• Duration: 1 hour
• Continuous improvement

Tools:
• Project Management: Jira/Linear
• Communication: Slack
• Documentation: Notion/Confluence
• Code Repository: GitHub
• Design: Figma

# 10. Post-Launch Roadmap

## Phase 2 (Months 4-6)

Add 20 more schemes

Regional languages: Marathi, Tamil, Telugu

Document upload and verification

Application tracking integration

SMS-based eligibility checks (no internet)

Advanced analytics dashboard

Scheme recommendation engine

Multi-scheme comparison tool

## Phase 3 (Months 7-12)

Mobile app (React Native)

Chatbot for FAQ and queries

Integration with state portals

Predictive analytics (scheme success rates)

Community forum

Video tutorials in regional languages

Blockchain for application tracking

AI-powered crop recommendations

## Scalability Targets

Year 1: 10,000 active users, 50 schemes
Year 2: 50,000 active users, 100 schemes
Year 3: 100,000+ active users, 150+ schemes